Procedure

Simultaneous Operations (SIMOPS)

[Enter Project Name]

| Document Number | Revision | Date |
| --- | --- | --- |
| RTPR-HSE-PRO-XXXX | Rev 0 | 30/06/2026 |

| Status | Name | Position | Signature |
| --- | --- | --- | --- |
| Originator | Ashleigh Phillips | [External] HSES Industry Partners |  |
| Reviewed | Kirsten Snyman | Snr Manager, CSP RioProjects |  |
| Reviewed | Matt Moroz | Snr Manager, HSES RioProjects |  |
| Approved | Greg Doyle | Vice President HSESC, SD&T |  |

Contents

0	How to Use This Document	3

0.1	Purpose of This Template	3

0.2	How This Document is Structured	3

0.3	Step-by-Step Completion Instructions	3

0.4	Pre-Issue Checklist	4

0.5	Document Relationships	4

1	Heading	6

Heading

INSTRUCTION: Read, action and delete this box before this procedure is issued. Delete the entire Section 0 before this document is submitted for review or approval. It must not appear in any approved version of this procedure.

0  How to Use This Document

This section explains the purpose of the template, how it is structured, the sequence for completing it and the checks required before it is issued. It must be read in full before any section of this document is completed. Delete Section 0 in its entirety before issue.

0.1  Purpose of This Template

This template supports the preparation of a project-specific Simultaneous Operations (SIMOPS) Procedure for projects delivered under an Owner-Led model. Under this model, Rio Tinto directly manages all project activities, and this procedure applies to all personnel on the project, including Rio Tinto staff and all contractor organisations.

This template is provided as a 90% draft. Fixed content reflects the minimum Rio Tinto requirement and must not be reduced. The remaining 10% covers role names, register locations, schedules and project-specific triggers, and must be completed by the project team before issue.

0.2  How This Document is Structured

This document contains four content types:

Fixed content is plain black text reflecting minimum Rio Tinto requirements. Fixed content must not be reduced, deleted or overridden.

[INSERT: placeholder text] appears in blue bold. Each placeholder must be replaced with accurate, project-specific information before issue.

Orange text marks specific who, what, when, or how detail included as a best practice suggestion. The project team may retain, modify, or replace orange detail.

0.3  Pre-Issue Checklist

Before submitting this document for review or approval, confirm all items below are complete, then delete this checklist together with the rest of Section 0.

| Check | Complete? |
| --- | --- |
| Cover page is complete including document number, revision, date and signatories | ☐ |
| All [INSERT:] placeholder text has been replaced with project-specific information | ☐ |
| All instruction boxes have been read, actioned and deleted | ☐ |
| All role titles match the actual project organisational structure | ☐ |
| All system and register locations are confirmed and inserted | ☐ |
| All workshop and meeting dates are confirmed against the project programme | ☐ |
| Related procedures in the References section are issued or being issued concurrently | ☐ |
| Section 17 (Source Requirements Traceability) will be deleted before final issue | ☐ |
| Section 16 (Project Localisation Edits) has been populated with all changes made during preparation | ☐ |
| Section 0 has been deleted in its entirety | ☐ |

1  Purpose and Scope

This section defines the purpose of this procedure, the project lifecycle phases within scope, and the obligations it establishes from project Execution through to Handover.

1.1  Purpose of This Document

This section states the purpose of this procedure and the requirements it establishes for the project.

This procedure defines requirements for identifying, planning, managing, and controlling simultaneous operations across the owner-led project. Simultaneous operations are defined as two or more work scopes occurring simultaneously in the same or adjacent areas, or involving the same or associated systems. In the owner-led model, RT holds direct responsibility for ensuring that SIMOPS risks are identified and controlled across all contractor organisations.

1.2  Scope of This Document

This section defines which activities and lifecycle phases are governed by this document.

This procedure applies to all Rio Tinto project personnel and all contractor organisations performing work under an Owner-Led project. It governs simultaneous operations (simops) from project Execution through to Handover.

[INSERT: scope qualifications] — note any activities, phases, or locations excluded from this procedure's scope

2  Roles and Responsibilities

This section defines the responsibilities for all project roles relevant to this procedure, covering the Rio Tinto project team and all contractor organisations. Responsibilities are aligned to governance, oversight, assessment execution, reporting, and control verification.

| Responsibilities | Company | Contractor | Section |
| --- | --- | --- | --- |
| Project Management |  |  |  |
| Holds overall accountability for project compliance with this procedure and approves this procedure and any material amendment. | ✓ |  |  |
| Accepts residual risk at the highest risk class level and authorises continuation where escalation is required. | ✓ |  |  |
| [INSERT: add further responsibilities as required] |  |  |  |
| HSE/CSP Management |  |  |  |
| Maintains and implements this procedure and confirms all activities meet its requirements before work proceeds. | ✓ | ✓ |  |
| Reviews and approves all required assessments, plans, and registers produced under this procedure. | ✓ | ✓ |  |
| Reports performance against this procedure at the agreed project HSESC performance meeting. | ✓ | ✓ |  |
| Reviews performance data, identifies trends, and incorporates systemic findings into corrective action programmes. | ✓ | ✓ |  |
| [INSERT: add further responsibilities as required] |  |  |  |
| Frontline Supervision |  |  |  |
| Ensures work crew compliance with this procedure before and during all relevant task executions. | ✓ | ✓ |  |
| Stops work when the requirements of this procedure cannot be met and notifies the HSESC Manager. | ✓ | ✓ |  |
| Confirms all personnel under their supervision are trained and competent before commencing relevant activities. | ✓ | ✓ |  |
| [INSERT: add further responsibilities as required] |  |  |  |
| All Project Personnel / Workers |  |  |  |
| Complies with the requirements of this procedure in all relevant work activities. | ✓ | ✓ |  |
| Reports any non-compliance with this procedure immediately to their supervisor. | ✓ | ✓ |  |
| [INSERT: add further responsibilities as required] |  |  |  |

3  Purpose and Scope

This section defines the purpose of this procedure, the simultaneous operations it governs, and the lifecycle phases and project boundaries within which it applies.

3.1  Purpose of This Document

This section states the purpose of this procedure, the framework it establishes, and the requirements it sets for managing simultaneous operations.

This procedure meets the following purpose requirements:

This procedure establishes the minimum requirements for identifying, planning, controlling, and coordinating simultaneous operations (SIMOPS) on this project, and applies to Rio Tinto and all Contractor organisations performing work in areas of concurrent activity.

This procedure governs the SIMOPS workshop process, the preparation and maintenance of the SIMOPS Plan, the development and application of the SIMOPS Matrix, and the conditions under which simultaneous work must be stopped or risk assessments revalidated.

Hazard analysis conducted during SIMOPS planning and execution is governed by the Risk Management Procedure, RTPR-HSE-PRO-0002. Permit to Work requirements during SIMOPS are governed by the Permit to Work Procedure, RTPR-HSE-PRO-0021. Changes to SIMOPS conditions that trigger a management of change process are governed by RTPR-HSE-PRO-0040. SIMOPS arising during the commissioning phase are governed by RTPR-HSE-PRO-0047.

3.2  Scope of This Document

This section defines which simultaneous operation activities and project phases are governed by this document.

This procedure applies the following scope requirements:

This procedure applies from the point at which simultaneous operations are first planned for this project and remains in effect until all concurrent work scopes in a given area have been completed or the project reaches handover.

This procedure applies to all areas of the project site where two or more work scopes, performed by any combination of Rio Tinto and Contractor organisations, are planned or occurring at the same time in spatial or operational proximity.

The simultaneous operation scenarios anticipated for this project are identified and documented in the SIMOPS Plan.

[INSERT: simops_scenarios_summary] — Identify all simultaneous operation scenarios anticipated for this project and insert into the SIMOPS Plan. Map each interface against the SIMOPS Matrix before any concurrent work commences.

4  SIMOPS Planning and Risk Assessment

This section defines the requirements for the SIMOPS workshop, hazard analysis obligations during planning and execution, and Permit to Work compliance across all simultaneous operations.

4.1  SIMOPS Workshop

This section defines the workshop requirements that must be met before any phase of work involving simultaneous operations commences.

A SIMOPS workshop must be conducted jointly with the Company and all Contractor organisations before any phase of work where simultaneous operations are planned. The workshop must identify potential conflicts, risks, and hazards arising from concurrent activities and must produce a SIMOPS Plan before simultaneous operations commence.

The SIMOPS workshop must address the following as a minimum:

The SIMOPS workshop agenda must cover:

Identification of all concurrent work scopes, their locations, and their planned durations.

Assessment of spatial and operational conflicts between simultaneous activities.

Review and agreement of controls, exclusion zones, and coordination arrangements for each identified interface.

Agreement of the permit issuing authority for all project phases where simultaneous permits may overlap.

Confirmation of the SIMOPS Matrix, Task Definitions, and Restrictions Table applicable to the project.

Review of lessons learned from previous SIMOPS on comparable Rio Tinto projects.

[INSERT: workshop_additional_agenda_items]

The SIMOPS workshop must be facilitated by

[INSERT: workshop_facilitator_role] — Insert the role responsible for facilitating the SIMOPS workshop, e.g. HSESC Manager or Construction Manager.

Workshop outputs, including the list of identified interfaces, agreed controls, and the draft SIMOPS Plan, must be documented and distributed to all participants within

[INSERT: workshop_output_distribution_timeframe] — Insert the required timeframe for distributing workshop outputs, e.g. five business days of workshop completion.

4.2  Hazard Analysis During Planning and Execution

This section defines the hazard analysis obligations that apply during both the planning and execution phases of all SIMOPS.

Hazard analysis must be conducted during both the planning and execution phases of all simultaneous operations. The methodology and risk matrix applied during SIMOPS hazard analysis are governed by the Risk Management Procedure, RTPR-HSE-PRO-0002.

As conditions change during execution, hazard analysis must be updated to reflect new interfaces and changing risk profiles. Updated hazard analysis outputs must be incorporated into the SIMOPS Plan before affected work resumes.

The criteria for revalidating risk assessments in response to changing SIMOPS conditions are defined in Section 3.3 of this procedure.

4.3  Permit to Work Compliance During SIMOPS

This section defines the PTW requirements that apply to all simultaneous operations, including overlapping permits in shared work areas.

All simultaneous operations must comply with the project Permit to Work system. No simultaneous operation may commence without all required permits being in place and active. Personnel must raise a permit via the site PTW system before commencing work, refer RTPR-HSE-PRO-0021.

Where simultaneous permits overlap in the same area, the permit issuing authority must review and authorise all concurrent permits before work commences. The permit issuing authority arrangements for this project are confirmed as follows:

[INSERT: permit_issuing_authority_simops] — Confirm the permit issuing authority arrangements for overlapping permits in SIMOPS areas. Define who holds the permit issuing authority role, how concurrent permits in the same area are coordinated, and the approval sequence required before simultaneous work commences. The PTW procedure owns permit types and roles — this section must define coordination and approval of simultaneous permits.

Permit types, permit roles, and the full PTW process are owned by RTPR-HSE-PRO-0021 and are not repeated here.

5  SIMOPS Plan

This section defines the requirements for preparing, maintaining, and applying the SIMOPS Plan, including minimum content, work stoppage conditions, revalidation criteria, and coordination meeting obligations.

5.1  SIMOPS Plan Preparation and Maintenance

This section defines when the SIMOPS Plan must be prepared and how it must be maintained as the work programme evolves.

A written SIMOPS Plan must be prepared for all identified simultaneous operations before work commences. The SIMOPS Plan must be maintained and updated throughout the work programme as activities, interfaces, and risk profiles change.

The SIMOPS Plan is owned by

[INSERT: simops_plan_owner_role] — Insert the role responsible for owning and maintaining the SIMOPS Plan, e.g. Construction Manager or HSESC Manager.

The SIMOPS Plan is stored in

[INSERT: simops_plan_location] — Insert the document management system location where the SIMOPS Plan is stored and controlled.

Where a change in SIMOPS conditions requires a management of change assessment, the process governed by RTPR-HSE-PRO-0040 applies before the updated plan is issued.

5.2  SIMOPS Plan Minimum Content

This section defines the minimum content that every SIMOPS Plan for this project must include.

The SIMOPS Plan must include the following minimum content:

The SIMOPS Plan must document:

Identification of all concurrent work scopes and their locations, including the organisations performing each scope.

Assessment of potential conflicts between simultaneous activities, referenced against the SIMOPS Matrix.

Applicable controls and exclusion zones for each identified interface.

The permit issuing authority for all project phases where simultaneous permits may overlap.

The SIMOPS coordination meeting schedule, including frequency, participants, chair, agenda template, and minutes distribution.

Communication protocols between work groups operating in areas of simultaneous activity.

An interface register cross-referencing each concurrent work scope with the relevant SIMOPS Matrix cell and applicable Restriction Table entry.

[INSERT: simops_plan_additional_content]

PROJECT COMPLETION: Develop the site-specific SIMOPS Matrix, Task Definitions, and Restrictions Table for this project and attach to or reference within the SIMOPS Plan. These cannot be carried over unchanged from previous projects. Define the SIMOPS coordination meeting schedule for this project — frequency, participants, chair, agenda template, and minutes distribution — and insert into the SIMOPS Plan.

5.3  Work Stoppage Due to SIMOPS Risk

This section defines the conditions under which work must stop due to SIMOPS-related risks and the authority and process that applies.

Work must cease in any area where a SIMOPS-related risk cannot be adequately controlled. The conditions that require immediate work stoppage are:

Work must stop when any of the following conditions exists:

A risk control identified in the SIMOPS Plan is not in place at the time work is due to commence or during execution.

Activities deviate from the approved SIMOPS Plan without prior re-assessment and authorisation.

A new interface or hazard arises during execution that is not covered by the current SIMOPS Plan.

The authority to call a SIMOPS-related work stoppage and the escalation process for resumption are defined as follows:

[INSERT: work_stoppage_authority_and_escalation] — Define the work stoppage authority and escalation process for SIMOPS-related stoppages: who can call a stop; who must be notified; and what the process is for resumption following a SIMOPS-triggered work stoppage.

Table: SIMOPS Work Stoppage Authority and Resumption Process

| Trigger Condition | Authority to Stop Work | Notification Required | Resumption Approval |
| --- | --- | --- | --- |
| Risk control not in place | [INSERT: role] | [INSERT: roles to be notified] | [INSERT: approval role and process] |
| Deviation from approved SIMOPS Plan | [INSERT: role] | [INSERT: roles to be notified] | [INSERT: approval role and process] |
| New interface or hazard not covered by plan | [INSERT: role] | [INSERT: roles to be notified] | [INSERT: approval role and process] |

All personnel on this project hold the right and obligation to stop work when a SIMOPS risk control is absent or a new unassessed hazard is identified. Work may not resume until the condition triggering the stoppage has been resolved and the resumption authority has confirmed the SIMOPS Plan controls are restored or updated.

All incidents and near misses arising from SIMOPS interfaces must be reported per project requirements, refer RTPR-HSE-PRO-0009.

5.4  Risk Assessment Revalidation

This section defines the criteria that require risk assessments to be revalidated in response to changing SIMOPS conditions.

Risk assessments supporting the SIMOPS Plan must be revalidated whenever the conditions on which they were based materially change. The criteria that require revalidation are:

Risk assessment revalidation is required when:

The scope of any simultaneous activity changes in a way that alters the nature or severity of an identified interface.

New work scopes are introduced into an active SIMOPS area that were not considered in the current risk assessment.

An incident or near miss occurs involving a SIMOPS interface, whether or not the event resulted in injury or damage.

The timing or sequencing of concurrent activities changes such that previously assessed separation or exclusion arrangements no longer apply.

Revalidation must be completed and the updated SIMOPS Plan issued before affected simultaneous activities resume. Where a scope change triggers the management of change process, the requirements of RTPR-HSE-PRO-0040 apply. Hazard analysis methodology used during revalidation is governed by RTPR-HSE-PRO-0002.

The role responsible for initiating and confirming risk assessment revalidation is

[INSERT: revalidation_responsible_role] — Insert the role responsible for initiating and confirming SIMOPS risk assessment revalidation, e.g. HSESC Manager.

5.5  SIMOPS Coordination Meetings

This section defines the requirements for regular coordination meetings between the Company and Contractor organisations in SIMOPS areas.

Regular SIMOPS coordination meetings must be held between the Company and all Contractor organisations operating in areas of simultaneous activity. Meeting frequency must be proportionate to the complexity of simultaneous operations and must be documented in the SIMOPS Plan.

The coordination meeting schedule for this project is defined as follows:

[INSERT: coordination_meeting_schedule] — Define the SIMOPS coordination meeting schedule for this project: frequency, participants, chair, agenda template, and minutes distribution. Insert into the SIMOPS Plan.

Table: SIMOPS Coordination Meeting Schedule

| Meeting Type | Frequency | Chair | Participants | Minutes Distribution | Location |
| --- | --- | --- | --- | --- | --- |
| SIMOPS Coordination Meeting | [INSERT: e.g. daily during peak concurrent activity, weekly during lower-intensity periods] | [INSERT: role] | [INSERT: roles and organisations required to attend] | [INSERT: distribution list and timeframe for minutes] | [INSERT: location or virtual platform] |
| text | suggested |

Meeting minutes must be recorded and stored in

[INSERT: meeting_minutes_storage] — Insert the document management system location where SIMOPS coordination meeting minutes are stored.

Action items arising from coordination meetings must be assigned to a named role, given a due date, and tracked to closure. Outstanding actions must be reviewed at the subsequent meeting.

6  SIMOPS Matrix

This section defines the requirements for the SIMOPS Matrix, including Task Definitions, Restriction Tables, site-specific development obligations, and the process for approving deviations from matrix parameters.

6.1  Purpose and Application of the SIMOPS Matrix

This section defines what the SIMOPS Matrix is, when it must be used, and the tools it must be applied with.

A SIMOPS Matrix must be implemented for all project sites where simultaneous operations occur. The SIMOPS Matrix is a reference tool used to determine whether activities can be performed simultaneously and under what conditions.

The SIMOPS Matrix must be used in conjunction with the following supporting tools:

The SIMOPS Matrix must be applied together with:

Task Definitions that describe each category of simultaneous activity included in the matrix.

Restriction Tables that define the conditions under which pairs of activities may or may not occur concurrently.

The SIMOPS Matrix, Task Definitions, and Restrictions Table for this project are attached to or referenced within the SIMOPS Plan. Before any concurrent work commences, each identified interface must be mapped against the relevant SIMOPS Matrix cell and the applicable Restriction Table entry confirmed.

6.2  Site-Specific Development Requirements

This section defines the requirement for site-specific development of the SIMOPS Matrix and the tools associated with it.

Each project site must develop its own Task Definitions, SIMOPS Matrix, and Restrictions Table, incorporating applicable regulatory requirements and site-specific operational considerations. Generic matrices from previous projects are not acceptable without site-specific review and adaptation.

PROJECT COMPLETION: Develop the site-specific SIMOPS Matrix, Task Definitions, and Restrictions Table for this project. These documents cannot be carried over unchanged from a previous project. Each must be reviewed against the specific concurrent work scopes, site layout, regulatory context, and operational interfaces applicable to this project before issue.

The site-specific SIMOPS Matrix for this project is

[INSERT: simops_matrix_document_reference] — Insert the document number and title of the site-specific SIMOPS Matrix for this project.

The Task Definitions document for this project is

[INSERT: task_definitions_document_reference] — Insert the document number and title of the Task Definitions document for this project.

The Restrictions Table for this project is

[INSERT: restrictions_table_document_reference] — Insert the document number and title of the Restrictions Table for this project.

Table: SIMOPS Matrix — Example Structure (project team to develop site-specific version)

| Activity (Row) | Activity (Column) | Simultaneous Permitted | Conditions / Restriction Table Reference | Approval Required |
| --- | --- | --- | --- | --- |
| [INSERT: Task Definition Category] | [INSERT: Task Definition Category] | [INSERT: Yes / No / Conditional] | [INSERT: Restriction Table reference or description of conditions] | [INSERT: approval role if conditional] |
| [INSERT: Task Definition Category] | [INSERT: Task Definition Category] | [INSERT: Yes / No / Conditional] | [INSERT: Restriction Table reference or description of conditions] | [INSERT: approval role if conditional] |

6.3  Deviations from the SIMOPS Matrix

This section defines the approval and documentation requirements for deviations from the SIMOPS Matrix or Restriction Tables.

Any deviation from the SIMOPS Matrix or Restriction Tables must be approved by the appropriate level of management before simultaneous activities proceed outside matrix parameters. All deviations must be documented and risk-assessed before the deviated activity commences.

The approval authority for matrix deviations on this project is defined as follows:

Table: SIMOPS Matrix Deviation Approval Authority

| Deviation Type | Approval Authority | Documentation Requirement | Risk Assessment Required |
| --- | --- | --- | --- |
| Conditional activity proceeding outside Restriction Table parameters | [INSERT: role] | [INSERT: form or register reference] | Yes — refer RTPR-HSE-PRO-0002 |
| Activity not included in the current SIMOPS Matrix | [INSERT: role] | [INSERT: form or register reference] | Yes — refer RTPR-HSE-PRO-0002 |
| {'text': 'Temporary relaxation of an exclusion zone defined in the Restrictions Table', 'suggested': True} | [INSERT: role] | [INSERT: form or register reference] | Yes — refer RTPR-HSE-PRO-0002 |

Where a matrix deviation involves a change to the approved SIMOPS Plan, the management of change process governed by RTPR-HSE-PRO-0040 must be initiated before the deviation is approved. The approved deviation must be recorded in the SIMOPS Plan and communicated to all affected work groups before work proceeds.

7  Definitions and Acronyms

The following terms are used throughout this procedure. Where a term is also used in other project HSESC procedures, the definition below applies consistently across the system.

| Term | Definition |
| --- | --- |
| SIMOPS | Simultaneous Operations — the concurrent execution of two or more activities, operations, or work scopes within the same area or on shared systems that have the potential to interact and create hazards not present when the activities are conducted independently. |
| PTW | Permit to Work — a formal documented system used to control non-routine work activities that present significant hazards, ensuring authorisation, risk controls, and communication are in place before work commences. |
| MoC | Management of Change — a systematic process to evaluate, approve, and communicate changes to facilities, equipment, processes, procedures, or organisational arrangements to ensure HSESC risks are identified and managed before implementation. |
| HSESC | Health, Safety, Environment, Security, and Communities — the integrated discipline framework governing all risk and compliance obligations on Rio Tinto owner-led projects. |
| HSE | Health, Safety, and Environment — the combined discipline area covering occupational health, safety management, and environmental protection obligations. |
| HAZID | Hazard Identification — a structured, facilitated study technique used to systematically identify potential hazards associated with operations, activities, or changes, including those arising from simultaneous operations. |
| HAZOP | Hazard and Operability Study — a structured and systematic examination of a planned or existing process or operation to identify and evaluate problems that may represent risks to personnel, equipment, or the environment, or prevent efficient operation. |
| JHA | Job Hazard Analysis — a task-level risk assessment technique that identifies hazards associated with each step of a specific job or task and establishes controls to eliminate or mitigate those hazards before work begins. |
| JSA | Job Safety Analysis — a systematic procedure that reviews job methods and uncovers hazards that may have been overlooked in the design of the plant, equipment, or process, equivalent in application to a Job Hazard Analysis. |
| RAM | Risk Assessment Matrix — a tool used to evaluate and rank risks by combining the likelihood of an event occurring with the consequence severity, in accordance with the Rio Tinto Risk Management Standard. |
| ALARP | As Low As Reasonably Practicable — the principle that residual risk must be reduced to a level where the cost of further reduction is grossly disproportionate to the benefit gained, consistent with Rio Tinto risk management requirements. |
| ITP | Inspection and Test Plan — a document that specifies the sequence of inspections, tests, and hold points required during construction, installation, or commissioning activities, which may interact with simultaneous operations. |
| P&ID | Piping and Instrumentation Diagram — an engineering drawing showing the interconnection of process equipment, piping, instrumentation, and control systems, used as a reference during SIMOPS planning to identify interface and isolation points. |
| OIM | Operations Interface Meeting — a scheduled coordination meeting held to review, plan, and communicate simultaneous operations activities, responsibilities, and controls between all parties involved in concurrent work. |
| PRO | Procedure — a documented, step-by-step instruction or process that defines how a specific activity or series of activities is to be carried out within the Rio Tinto project management system. |
| RT | Rio Tinto — the parent organisation whose standards, frameworks, and requirements govern the development and application of all HSESC procedures on owner-led projects. |
| RTPR | Rio Tinto Project — the project-specific designation prefix used to identify procedures, documents, and references developed under the Rio Tinto owner-led project management system. |
| SMP | SIMOPS Management Plan — a project-level plan that establishes the overall strategy, governance framework, roles and responsibilities, communication protocols, and control measures for managing simultaneous operations throughout the project lifecycle. |
| EPC | Engineering, Procurement, and Construction — the project delivery model under which a contractor is responsible for the design, procurement of materials, and physical construction of a facility, often creating SIMOPS interfaces with owner-led activities. |
| PPE | Personal Protective Equipment — equipment worn by personnel to minimise exposure to hazards that cannot be eliminated or adequately controlled by other means, forming part of the hierarchy of controls applied during SIMOPS. |
| MOC | Management of Change — refer to MoC. This alternate capitalisation refers to the same formal process for evaluating and approving changes that may affect SIMOPS conditions, interfaces, or risk profiles. |
| SOP | Standard Operating Procedure — a documented procedure prescribing the authorised and required method for performing a routine or non-routine operational task, which may be invoked or suspended during SIMOPS activities. |
| TRA | Task Risk Assessment — a site-level, pre-task risk evaluation conducted by the work crew immediately before commencing a specific activity, used to verify that controls identified during SIMOPS planning remain applicable to actual site conditions. |
| LOTO | Lockout/Tagout — an energy isolation procedure requiring physical locks and tags to be applied to energy sources to prevent accidental energisation of equipment during maintenance or simultaneous operations in adjacent areas. |
| SIMOPS Matrix | A structured decision-support tool used during SIMOPS planning that maps concurrent activities against each other to evaluate compatibility, identify conflict or risk interactions, and assign required controls or restrictions for each activity combination. |
| [INSERT: add project-specific terms] | [INSERT: definition] |

8  References and Source Information

This section lists the internal and external documents this procedure relies on. This section remains in the procedure once published. Where a referenced document is updated, this procedure is reviewed to confirm the reference remains current.

| Document | Reference | Type |
| --- | --- | --- |
| Risk Management Procedure | RTPR-HSE-PRO-0002 | Internal procedure |
| Permit to Work Procedure | RTPR-HSE-PRO-0021 | Internal procedure |
| Management of Change Procedure | RTPR-HSE-PRO-0040 | Internal procedure |
| Commissioning Safety Procedure | RTPR-HSE-PRO-0047 | Internal procedure |
| Rio Tinto Risk Management Standard | RT Risk Management Standard | External RT |
| Rio Tinto Risk Management Standard — Appendix C, Section C-1: Risk Assessment Criteria and Matrix | RT Risk Management Standard, Appendix C, C-1 | External RT |
| Rio Tinto Health, Safety and Environment Management System Framework | RT HSEMS Framework | External RT |
| Rio Tinto Contractor Management Standard | RT Contractor Management Standard | External RT |
| ISO 31000:2018 — Risk Management: Guidelines | ISO 31000:2018 | External framework |
| AS/NZS 4804:2001 — Occupational Health and Safety Management Systems: General Guidelines on Principles, Systems and Supporting Techniques | AS/NZS 4804:2001 | External framework |
| IOGP Report 454 — Life-Saving Rules | IOGP 454 | External framework |
| IOGP Report 376 — Simultaneous Operations Guidelines | IOGP 376 | External framework |
| [INSERT: further referenced document, where applicable] | [INSERT: reference] | [INSERT: type] |

9  Project Localisation Edits

This section captures the project-specific edits made to this document during preparation. This section stays in the document once published and is updated at each document revision. Record all additions, deletions, and wording changes from the original template.

Records of wording changes

| Description of the Change | Section |
| --- | --- |
| [INSERT: description of change] | [INSERT: section] |
| [INSERT: description of change] | [INSERT: section] |
| [INSERT: description of change] | [INSERT: section] |

Records of new content additions

| Description of the Change | Section |
| --- | --- |
| [INSERT: description of change] | [INSERT: section] |
| [INSERT: description of change] | [INSERT: section] |
| [INSERT: description of change] | [INSERT: section] |

Records of content removal

| Description of the Change | Section |
| --- | --- |
| [INSERT: description of change] | [INSERT: section] |
| [INSERT: description of change] | [INSERT: section] |
| [INSERT: description of change] | [INSERT: section] |

REMOVABLE SECTION — Source Requirements Traceability. Delete this entire section before the document is issued for approval. It must not appear in any approved version of this document. Table A records requirements addressed in this procedure. Table B records requirements not fully addressed, with written justification for each.

10  Source Requirements Traceability (DELETE BEFORE ISSUE)

10.1  Requirements Addressed in This Procedure

| Section | Source | Requirement | Status |
| --- | --- | --- | --- |
| [INSERT: section] | Appendix C C-2 §63.0.1 | Requires a SIMOPS workshop conducted jointly with the Company and all Contractor organisations before any phase of work where simultaneous operations are planned, producing a SIMOPS Plan before simultaneous operations commence. | Full |
| [INSERT: section] | Appendix C C-2 §63.0.2 | Requires hazard analysis during both the planning and execution phases of all SIMOPS, updated as conditions change during execution. | Full |
| [INSERT: section] | Appendix C C-2 §63.0.3 | Requires compliance with the project PTW system during all SIMOPS activities, with the permit issuing authority reviewing and authorising all concurrent permits in the same area before work commences. | Full |
| [INSERT: section] | Appendix C C-2 §63.0.4 | Requires a written SIMOPS Plan for all identified simultaneous operations, prepared before work commences and maintained throughout the work programme. | Full |
| [INSERT: section] | Appendix C C-2 §63.0.5 | Requires the SIMOPS Plan to include minimum content covering concurrent work scope identification, conflict assessment, controls and exclusion zones, permit issuing authority, coordination meeting schedule, and communication protocols. | Full |
| [INSERT: section] | Appendix C C-2 §63.0.6 | Defines conditions under which work must be stopped due to SIMOPS-related risks, including where controls are absent, activities deviate from the approved plan, or new unplanned hazards arise. | Full |
| [INSERT: section] | Appendix C C-2 §63.0.7 | Defines criteria for risk assessment revalidation when SIMOPS conditions change, including scope changes, introduction of new work scopes, or an incident or near miss involving a SIMOPS interface. | Full |
| [INSERT: section] | Appendix C C-2 §63.0.8 | Requires regular SIMOPS coordination meetings between the Company and all Contractor organisations in areas of simultaneous activity, with frequency proportionate to operational complexity. | Full |
| [INSERT: section] | Appendix C C-2 §63.0.9 | Requires implementation of a SIMOPS Matrix for all project sites where simultaneous operations occur, used as a reference tool to determine whether activities can be performed simultaneously and under what conditions. | Full |
| [INSERT: section] | Appendix C C-2 §63.1.1 | Requires the SIMOPS Matrix to be used in conjunction with Task Definitions and Restriction Tables that define the conditions under which pairs of activities may or may not occur concurrently. | Full |
| [INSERT: section] | Appendix C C-2 §63.1.2 | Requires each site to develop its own Task Definitions, SIMOPS Matrix, and Restrictions Table incorporating regulatory requirements and site-specific considerations; generic matrices from previous projects are not acceptable without site-specific review. | Full |
| [INSERT: section] | Appendix C C-2 §63.1.3 | Requires that deviations from the SIMOPS Matrix or Restriction Tables are approved by the appropriate level of management before simultaneous activities proceed outside matrix parameters, and that deviations are documented and risk-assessed. | Full |

10.2  Requirements Not Fully Addressed in This Procedure

List any requirements from the external sources above that are not fully addressed in this document, with a specific written justification for each. Acceptable justifications: (a) the requirement is owned by a named standalone procedure cross-referenced here; (b) excluded by a specific business decision endorsed by project leadership, named here; or (c) addressed through an operational control outside this document, identified here.

| Requirement Not Covered | Source | Justification |
| --- | --- | --- |
| [INSERT: description of requirement not covered] | [INSERT: source and clause] | [INSERT: specific written justification] |